## Team
Initials | First | Last | Email | GitHub Username | ScrumMaster
dm | Deep | Manek | dmanek@stevens.edu | dpmanek | Yes
am | Anish | Malhotra | amalhot6@stevens.edu | SeeAnish | No
st | Sakshi | Tonde | stonde@stevens.edu | stonde | No
sn | Surya | Nediyadeth | snediyad@stevens.edu | Surya7612 | No
jp | Janan | Patel | jpatel7@stevens.edu | jananpatel6243 | No
GitHub Repository: | https://github.com/dpmanek/CS_555_C_Atom.git
Game's Story Line | It's suppertime, and an adorable baby monkey is being fed by a Mama Monkey. However, a group of hunters emerges out of nowhere and kidnaps the infant monkey. This humorous game tells the story of an enraged mother attempting to reclaim her child by following after the hunters through the jungle while avoiding numerous obstacles.
Motive | Using various humorous background sounds that will ease up users anxiety and help calm user down
Inspiration | Hidden Folks - Official Trailer - YouTube
Platform | Python - Pygame

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US04 | Nature Inspired Theme | sn,dm,jp,st,am | Coding
| T04.03 | Create Obstacles | sn | In Progress | 70 | 1
| T04.04 | Apply Collisons | dm | In Progress | 50 | 2
| T04.05 | Adding Texts | st | In Progress | 20 | 1
| T04.06 | Add Highscore and Health meter | st | In Progress | 40 | 1
| T04.08 | Adding Menu Option | am | In Progress | 50 | 2
| T04.10 | Adding Animations to the Obstacles | dm,am | In Progress | 120 | 3

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2022-02-18 | 13 |  | 0
2022-03-01 | 12 | 1 | 762 | 480 | 95.25

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US04 | Nature Inspired Theme | sn,dm,jp,st,am |  | 610 | 18
T04.01 | Create Initial set-up/background | sn |  | 80 | 2 | 251 | 2 | Yes
T04.02 | Create Avatar | dm |  | 50 | 2 | 46 | 1 | Yes
T04.03 | Create Obstacles | sn,dm | Pending | 70 | 1
T04.04 | Apply Collisons | sn,jp | Pending | 50 | 2
T04.05 | Adding Texts | st,am | Pending | 20 | 1
T04.06 | Add Highscore and Health meter | st,am | Pending | 40 | 1
T04.07 | Adding Buttons(Start/Stop/Restart) | am |  | 30 | 1 | 68 | 1 | Yes
T04.08 | Adding Menu Option | st,jp | Pending | 50 | 2
T04.09 | Adding Animations to the Platforms | st |  | 100 | 3 | 120 | 2 | Yes
T04.10 | Adding Animations to the Obstacles | st,sn | Pending | 120 | 3
T04.11 | Creating Shooter | jp |  | 50 | 2 | 277 | 2 | Yes
Things you want to keep Doing
1 | Having Regular Standup
2 | Learn Pygame
3 | Put more efforts
Things you want to Avoid Doing in Sprint
1 | Talking on Whatsapp channel than Slack
2 | Committing code on github at the end moment

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US04 | Nature Inspired Theme
T04.03 | Create Obstacles | sn | In Progress | 70 | 1
T04.04 | Apply Collisons | dm | In Progress | 50 | 2
T04.05 | Adding Texts | st | In Progress | 20 | 1
T04.06 | Add Highscore and Health meter | st | In Progress | 40 | 1
T04.08 | Adding Menu Option | am | In Progress | 50 | 2
T04.10 | Adding Animations to the Obstacles | dm,am | In Progress | 120 | 3
US05 | Control Avatar
T05.01 | Adding Movements to the avatar | jp |  | 80 | 1
US06 | Deflect Obstacles
T06.01 | Analyzing the obstacles and allow movements for the avatar | jp |  | 100 | 1
US08 | Maintaining Health/Lives
T08.01 | Applying AI to operate the Health Meter | sn |  | 300 | 2
T08.02 | Applying AI to recover the lost Health from Health Packages | sn |  | 250 | 2
T08.03 | Stopping the game when Health Meter downs to 0 | st,sn |  | 250 | 1
US03 | Game Controls
T03.01 | Creating Window Screen | st |  | 30 | 1
T03.02 | Adding texts and Images | st |  | 30 | 1
T03.03 | Adding Button for Opening/Closing the window | am |  | 80 | 2

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Stories
Story ID | Story Name | Story Description | Priority
US01 | Choose Username | As a Player, I want to enter a username for the Monkey Avatar | 5
US02 | Toggling between the Options | As a Player, I want to select between the options on the front page. | 5
US03 | Game Controls | As a Player, I want to understand the game controls | 4
US04 | Nature Inspired Theme | As a Player, I want to experience the nature-theme background. | 1
US05 | Control Avatar | As a Player, I want to control my avatar in the game using my Keyboard | 1
US06 | Deflect Obstacles | As a Player, I want to compete with the enemies and avoid obstacles. | 2
US07 | Play Sounds | As a Player, I want to experience the humourous sound effects of the game. | 1
US08 | Maintaing Health/Lives | As a Player, I want to regain the lost health to continue my game. | 3
US09 | Game Completion | As a Player, I want to complete the game. | 3
US10 | Restart & Quit | As a Player, I want to restart and quit the game. | 3
US11 | Scores | As a Player, I want to keep a record of my high scores. | 4
US12 | Notifications | As a Player, I want to get reminders for playing the game. | 2
Note: 1=highest priority and 5=lowest priority
Completed
In-progress
Pending