## Team
Initials | First | Last | Email | GitHub Username | ScrumMaster
fe | Farah | Elkourdi | felkourd@stevens.edu | felkourdi
jc | Jose | Cruz | jcruz11@stevens.edu | jjzcru
ks | Kavish | Sanghvi | ksanghv1@stevens.edu | kavishsanghvi | Scrum Master
vk | Viyeta | Kansara | vkansara@stevens.edu | viyeta
vl | Vandan | Lakhani | vlakhani@stevens.edu | Vandan1611
|  |  | GitHub Repository: | ssw555tm012021Fall | https://github.com/ssw555tm012021Fall
|  |  | Kanban URL: | https://github.com/ssw555tm012021Fall/halcyon-api/projects/4

## Backlog
Sprint | Story ID | Story Name | Owner | Status

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2021-09-22 | 13
Sprint 1 | 2021-10-12 | 10 | 3 | 1187 | 3000 | 23.74
Sprint 2 | 2021-10-25 | 5 | 5 | 1853 | 2220 | 18
Sprint 3 | 2021-11-08 | 2 | 3 | 1837 | 2820 | -0.3
Sprint 4 | 2021-11-29 | 0 | 3 | 1330 | 5100 | -6

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Implement sign-up page | jc, fe, ks | complete | 362 | 7 | 131 | 6
T01.01 | Design user-interface | jc | complete | 0 | 1 |  | 1 | 2021-09-28
T01.02 | Implement the design | jc | complete | 300 | 1 | 21 | 1 | 2021-09-29
T01.03 | Create table for the sign-up | ks | complete | 2 | 1 | 15 | 1 | 2021-09-29
T01.04 | Implement email validation | ks | complete | 50 | 2 | 7 | 1 | 2021-10-05
T01.05 | Implement the end point for sign-up | fe | complete | 10 | 2 | 88 | 2 | 2021-10-05
T01.06 | Sign-up email template | fe | complete | 70 | 1 | 100 | 1 | 2021-10-03
T01.07 | Resend verification code API | fe | complete | 50 | 1 | 90 | 1 | 2021-10-08
T01.08 | Confirm verification code API | fe | complete | 50 | 1 | 70 | 1 | 2021-10-08
US02 | Implement login page | jc, vk | complete | 510 | 9 | 454 | 19
T02.01 | Design user-interface | jc | complete | 0 | 1 |  | 1 | 2021-09-28
T02.02 | Implement the design | jc | complete | 300 | 1 | 21 | 1 | 2021-09-29
T02.03 | implement architecture | vk | complete | 200 | 5 | 406 | 12 | 2021-10-04
T02.04 | Implement the end point for login | vk | complete | 10 | 2 | 27 | 5 | 2021-10-04
US03 | Implement breakout rooms | jc, fe, vk | complete | 807 | 5 | 502 | 21
T03.01 | Design user-interface | jc | complete | 0 | 3 | 0 | 1 | 2021-09-28
T03.02 | Implement the design | jc | complete | 800 | 1 | 65 | 1 | 2021-10-03
T03.03 | Create tables for scheduling system | fe | complete | 7 | 1 | 20 | 1 | 2021-10-03
T03.04 | Implement time details API | vk | complete | 100 | 5 | 166 | 10 | 2021-10-09
T03.05 | Implement Room scheduling restrictions | vk | complete | 1 | 1 | 1 | 2 | 2021-10-09
T03.06 | Implement the booking system API | ks | complete | 100 | 4 | 250 | 6 | 2021-10-10
T03.07 | Implement cancel API | vk | complete | 100 | 4 | 113 | 1 | 2021-10-10
T03.08 | Implement update API | vk | complete | 100 | 4 | 215 | 3 | 2021-10-10
T03.09 | Implement reading user reservation details API | fe | complete | 60 | 2 | 68 | 2 | 2021-10-10
T03.10 | Travis CI integration and continuous deployment to Heroku | vk | complete | 25 | 1 | 38 | 2 | 2021-10-11
T03.11 | Show rooms API | fe | complete | 50 | 1 | 40 | 1 | 2021-10-10
US04 | Play music | jc | complete | 800 | 3 | 50 | 2 | 2021-10-03
T04.01 | Design user-interface | jc | complete | 0 | 1 | 0 | 1 | 2021-09-28
T04.02 | Implement the design | jc | complete | 800 | 2 | 50 | 1 | 2021-10-03
US05 | Guided meditation | jc | complete | 800 | 3 | 50 | 2 | 2021-10-03
T05.01 | Design user-interface | jc | complete | 0 | 1 | 0 | 1 | 2021-09-28
T05.02 | Implement the design | jc | complete | 800 | 2 | 50 | 1 | 2021-10-03
Things to continue
1 | Create specification of API
2 | Create file structure
Things to avoid
1 | Work simultaneously on the same file without structure
2 | Implement tests at the end of the sprint
3 | Not dividing detailed work at the start of sprint

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Notes
US04 | Play music |  |  | 375 | 10 | 518 | 12
T04.01 | Create database for music | fe | complete | 5 | 1 | 10 | 1 | 2021-10-14
T04.02 | Add music files in the hosting services | fe | complete | 0 | 2 | 0 | 1 | 2021-10-14
T04.03 | Implement the API for fetching music | fe | complete | 30 | 1 | 85 | 1 | 2021-10-22 | Test-driven development (TDD)
T04.04 | Implement the API for playing the music | fe | complete | 40 | 2 | 68 | 1 | 2021-10-22 | TDD & Pair programming (Viyeta)
T04.05 | Implement the player for music | jc | complete | 300 | 4 | 355 | 8 | 2021-10-19
US05 | Guided meditation |  |  | 275 | 7 | 508 | 5
T05.01 | Create database for meditation | fe | complete | 5 | 1 | 0 | 0 | 2021-10-14
T05.02 | Add meditation files in the hosting services | fe | complete | 0 | 1 | 0 | 1 | 2021-10-14
T05.03 | Implement the API for fetching meditation | fe | complete | 30 | 1 | 85 | 1 | 2021-10-22 | Test-driven development (TDD)
T05.04 | Implement the API for playing the meditation | fe | complete | 40 | 2 | 68 | 1 | 2021-10-22 | TDD & Pair programming (Viyeta)
T05.05 | Implement player for meditation | jc | complete | 200 | 2 | 355 | 2 | 2021-10-22
US07 | Notification to take break at fix interval every day |  |  | 290 | 10 | 349 | 9
T07.01 | Create database for break intervals | vk | complete | 10 | 1 | 9 | 1 | 2021-10-14
T07.02 | Implement API for break notification | vk | complete | 150 | 5 | 165 | 5 | 2021-10-24
T07.03 | Design user-interface | jc | complete | 0 | 2 | 0 | 1 | 2021-10-23
T07.04 | Implement the design | jc | complete | 100 | 1 | 175 | 2 | 2021-10-24
T07.05 | Test Cases | vk | complete | 30 | 1 | 50 | 3 | 2021-10-25
US12 | Notification to drink water at fix interval every day |  |  | 260 | 8 | 234 | 5
T12.01 | Create database for water reminder | vk | complete | 10 | 1 | 9 | 1 | 2021-10-14
T12.02 | Implement API for water reminder notification | vk | complete | 150 | 5 | 50 | 1 | 2021-10-24
T12.03 | Design user-interface | jc | complete | 0 | 1 | 0 | 1 | 2021-10-24
T12.04 | Implement the design | jc | complete | 100 | 1 | 175 | 2 | 2021-10-24
US11 | Set goals |  |  | 510 | 15 | 244 | 6
T11.01 | Create database for goals | ks | complete | 10 | 1 | 4 | 1 | 2021-10-23
T11.02 | Implement API for goals | ks | in-progress | 200 | 8 | 240 | 5
T11.03 | Design user-interface | jc | pending | 0 | 4
T11.04 | Implement the design | jc | pending | 300 | 2
US10 | Awards for activities |  |  | 560 | 12
T10.01 | Create database for awards | vl | in-progress | 10 | 1
T10.02 | Implement API for awards | vl | in-progress | 250 | 5
T10.03 | Design user-interface | jc | pending | 0 | 4
T10.04 | Implement the design | jc | pending | 300 | 2
Things to continue
1 | Create specification of API
2 | Create file structure
Things to avoid
1 | Work simultaneously on the same file without structure
2 | Implement tests at the end of the sprint
3 | Not dividing detailed work at the start of sprint
4 | check PR before merging
5 | Confirm team approval before any task

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US 10 | Set goals |  |  | 510 | 15 | 244 | 6
T10.01 | Create database for goals | ks | complete | 10 | 1 | 4 | 1 | 2021-10-23
T10.02 | Implement API for goals | ks | in-progress | 200 | 8 | 340 | 8 | 2021-11-08
T10.03 | Design user-interface | jc | pending | 0 | 4 | 0 | 2 | 2021-10-29
T10.04 | Implement the design | jc | pending | 300 | 2 | 287 | 4 | 2021-10-29
US 09 | Awards for activities |  |  | 560 | 12 | 0 | 0
T09.01 | Create database for awards | ks | pending | 10 | 1
T09.02 | Implement API for awards | ks | pending | 250 | 5
T09.03 | Design user-interface | jc | pending | 0 | 4
T09.04 | Implement the design | jc | pending | 300 | 2
US08 | Action recommendation for moods |  |  | 275 | 8 | 0 | 0
T08.01 | Research to understand how to implement | fe | complete | 0 | 2 | 0 | 5 | 2021-10-28
T08.02 | Create database for actions | jc | complete | 15 | 2 | 10 | 1 | 2021-10-26
T08.03 | Implement API for moods | fe | complete | 60 | 2 | 78 | 1 | 2021-11-07
T08.04 | Design user-interface | jc | complete | 0 | 2 | 0 | 2 | 2021-11-04
T08.05 | Implement the design | jc | complete | 200 | 2 | 144 | 2 | 2021-11-04
US07 | Personality detection |  |  | 200 | 7 | 0 | 0
T07.01 | Research to understand how to implement | vk | complete | 0 | 5 | 0 | 5 | 2021-10-26
T07.02 | Create database for actions | vk | complete | 10 | 1 | 9 | 2 | 2021-10-26
T07.03 | Implement API for personality detection | vk | complete | 400 | 24 | 300 | 10 | 2021-11-07
T07.04 | Design user-interface | jc | pending | 0 | 3 | 0 | 2 | 2021-11-04
T07.05 | Implement the design | jc | pending | 200 | 4 | 665 | 2 | 2021-11-04
Things to continue
1 | Create specification of API
2 | Create file structure
Things to avoid
1 | Work simultaneously on the same file without structure
2 | Implement tests at the end of the sprint
3 | Not dividing detailed work at the start of sprint
4 | check PR before merging

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US 09 | Awards for activities |  |  | 560 | 12 | 711 | 7
T09.01 | Create database for awards | ks | complete | 10 | 1 | 10 | 1 | 2021-11-13
T09.02 | Implement API for awards | ks | complete | 250 | 5 | 593 | 4 | 2021-11-22
T09.03 | Design user-interface | jc | complete | 0 | 4 | 0 | 1 | 2021-11-13
T09.04 | Implement the design | jc | complete | 300 | 2 | 108 | 1 | 2021-11-13
US08 | Action recommendation for moods |  |  | 61 | 2 | 21 | 2
T08.06 | Update database for depression action | jc | complete | 1 | 1 | 1 | 1 | 2021-11-08
T08.07 | Implement API to set if user is depressed | fe | complete | 60 | 1 | 20 | 1 | 2021-11-11
US12 | Face ID signin |  |  | 300 | 54 | 598 | 76
T12.01 | Configure Face ID login | jc | complete | 300 | 6 | 598 | 4 | 2021-11-21
T12.02 | Research implementation | vk | complete | 0 | 48 | 0 | 72 | 2021-11-19
Things we love in the project
1 | Flexibility to work in Agile management
2 | Core features of the application
3 | Practical implementation of the concepts learned in the lectures
Lessons learnt from the project
1 | Experienced real-world Agile team work style
2 | Teamwork and management
3 | Team meetings and daily update
4 | Help team members

## Stories
Story ID | Story Name | Priority | Story Description
US01 | Implement sign-up page | 5 | As a user, I want to signup so that I can use the mental wellness web app
US02 | Implement sign-in page | 5 | As a user, I want to use the app so that I can be mentally fit and track my health data
US03 | Implement meditation rooms | 1 | As a user, I want to access the meditation room so that I can take break to relax
US04 | Play music | 2 | As a user, I want to play music so that I can relax
US05 | Guided meditation | 3 | As a user, I want someone to assist me how to medidate so that I do not get lost in my own thoughts
US06 | Notification to take break at fix interval every day | 3 | As a user, I want to be reminded that I need to take breaks so that I don't forget
US07 | Personality detection | 4 | As a user, i want to know what is my personality type so that I can get a more accurate suggestions from the application
US08 | Action recommendation for moods | 2 | As a user, I want to get recommendation depending on my mood so that I can get back to my usual mood
US09 | Awards for activities | 3 | As a user, I want to know what are the awards so that I can get those awards
US10 | Set goals | 3 | As a user, i want to keep tracks of the progress that I have so that i keep my motivation
US11 | Notification to drink water at fix interval every day | 3 | As a user, I want to be reminded that I need to drink water so that I keep hydrated
US12 | Face ID sign-in | 5 | As a user, I want to access the mental wellness web app using face ID
Note: 1=highest priority and 5=lowest priority
Completed
In-progress
Pending

## Test case 1
Build | Module | Test Scenario Name | Test Scenario ID | Test Scenario Summary | Test Case ID | Summary | Priority | Execution Type | Pre- Condition | Detailed Steps | Post Condition | Expected Result
Build 1.0 | Application | Sign-Up Page | TS_001 | Verify the functionality of Sign-up Page | TC_001_01 | Verify that, after successfully signing up into the application user can use mental wellness web app. | Low | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter fill up all the fields of sign-up form. 4. User click on sign up button. | After successfully signing up into the application user must be able to use mental wellness web app. | After successfully signing up into the application user should be able to use mental wellness web app.
Build 1.0 | Application | Sign-In Page | TS_002 | Verify the functionality of Sign-In Page | TC_002_01 | Verify that, application help its users to keep track of their health data. | Low | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. Verify that after successfully signing into the application user can view his/her health data. | Application must help its users to keep track of their health data. | Application should help its users to keep track of their health data.
Build 1.0 | Application | Breakout Rooms | TS_003 | Verify the functionality of Breakout Rooms | TC_003_01 | Verify that user can use the breakout room to access the meditation room. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, User can use the breakout room to access the meditation room. | User must use the breakout room to access the meditation room. | User should use the breakout room to access the meditation room.
Build 1.0 | Application | Breakout Rooms | TS_003 | Verify the functionality of Breakout Rooms | TC_003_02 | Verify that by accessing the meditation room users can relax for the specific amount of period. i.e. 30 minutes | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, By accessing the meditation room users must relax for the specific amount of period. | By accessing the meditation room users must relax for the specific amount of period. | By accessing the meditation room users should be able to relax for the specific amount of period.
Build 1.0 | Application | Play Music | TS_004 | Verify the functionality of Play Music | TC_004_01 | Verify that user can successfully play music. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, whether or not user is able to play music or not. | User must successfully play music. | User should be able to successfully play music.
Build 1.0 | Application | Play Music | TS_005 | Verify the functionality of Guided Meditation | TC_005_01 | Verify that application helps the user in a process that how can he/she medicate himself/herself. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, there is some guidance in the application which can help the user in medication. | Application must help the user in a process that how can he/she medicate himself/herself. | Application should be able to help the user in a process that how can he/she medicate himself/herself.
Build 1.0 | Application | App Notifications | TS_006 | Verify the functionality of App Notifications | TC_006_01 | Verify that application has a 'break' reminder notification. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, application has a break reminder notification. | Application must have break reminder notification. | Application should has a break reminder notification.
Build 1.0 | Application | App Notifications | TS_006 | Verify the functionality of App Notifications | TC_006_02 | Verify that application has a 'drink water' reminder notification. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, application has a 'drink water' reminder notification. | Application must have 'drink water' reminder notification. | Application should has a 'drink water' reminder notification.
Build 1.0 | Application | Personality Detection | TS_007 | Verify the functionality of Personality Detection | TC_007_01 | Verify that application helps its user to get to know about their personality. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, application helps its user to get to know about their personality. | Application must helps its user to get to know about their personality. | Application should helps its user to get to know about their personality.
Build 1.0 | Application | Personality Detection | TS_007 | Verify the functionality of Personality Detection | TC_007_02 | Verify that by depicting the user's personality, application can give personality related suggestions to its user. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, application can give personality related suggestions to its user. | By depicting the user's personality, application must give personality related suggestions to its user. | By depicting the user's personality, application should be able to give personality related suggestions to its user.
Build 1.0 | Application | Action Recommendation for Mood | TS_008 | Verify the functionality of Action Recommendation for Mood | TC_008_01 | Verify that by depicting the user's mood, application can give recommendations to its users. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, application must be able to give recommendations to its users. | By depicting the user's mood, application must be able to give recommendations to its users. | By depicting the user's mood, application should be able give recommendations to its users.
Build 1.0 | Application | Awards to activities | TS_009 | Verify the functionality of Awards to activities | TC_009_01 | Verify that application should suggest new/old rewards to its user. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, whether or not application suggest new/old rewards to its user. | Application must suggest new/old rewards to its user. | Application should be able to suggest new/old rewards to its user.
Build 1.0 | Application | Awards to activities | TS_009 | Verify the functionality of Awards to activities | TC_009_02 | Verify that user should be able to get all rewards once he/she achieve a specific target. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, after achieving a specific target user can claim his/her rewards. | User must get all rewards once he/she achieve a specific target. | User should be able to get all rewards once he/she achieve a specific target.
Build 1.0 | Application | Set Goals | TS_010 | Verify the functionality of Set Goals | TC_010_01 | Verify that user can keep track of his/her progress in the application. | Medium | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application homepage. 3. User enter the username and password in the sign-In form. 4. User successfully logged into the application. 5- Now verify that, whether or not user keep track record of his/her progress. | User must keep track of his/her progress in the application. | User should be able to keep track of his/her progress in the application.

## Test case 2
Build | Module | Test Scenario Name | Test Scenario ID | Test Scenario Summary | Test Case ID | Summary | Priority | Execution Type | Pre- Condition | Detailed Steps | Post Condition | Expected Result
Build 1.0 | Application | Play Music | TS_01 | Verify the functionality of Play Music | TC_01_01 | Verify that there must be a database for the music. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application. 3. Now verify that, there has been a database for the music. | There must be a database for the music. | There should be a database for the music.
Build 1.0 | Application | Play Music | TS_01 | Verify the functionality of Play Music | TC_01_02 | Verify that music files are being successfully added in the hosting services. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application. 3. User add the music files. 4. Now verify that music files are being successfully added in the hosting services. | Music files must be successfully added in the hosting services. | Music files should be successfully added in the hosting services.
Build 1.0 | Application | Play Music | TS_01 | Verify the functionality of Play Music | TC_01_03 | Verify that API is implemented successfully for fetching the music. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application. 3. User selects a music file. 4. Verify that, API is successfully implemented and user can fetch the music file. | API must implemented successfully for fetching the music. | API should be implemented successfully for fetching the music.
Build 1.0 | Application | Play Music | TS_01 | Verify the functionality of Play Music | TC_01_04 | Verify that API is implemented successfully for playing the music. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application. 3. User selects a music file. 4. Verify that, API is successfully implemented and user can play that music file successfully. | API must implemented successfully for playing the music. | API should be implemented successfully for playing the music.
Build 1.0 | Application | Play Music | TS_01 | Verify the functionality of Play Music | TC_01_05 | Verify that player for the music is implemented successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User navigates to the web application. 3. User selects a music file. 4. Verify that, player for the music is implemented successfully. | Player for the music must implemented successfully. | Player for the music should be implemented successfully.
Build 1.0 | Application | Guided Meditation | TS_02 | Verify the functionality of Guided Meditation | TC_02_01 | Verify that there must be a database for the meditation. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the meditation section. 4. Now verify that there must be a database for meditation. | There must be a database for the meditation. | There should be a database for the meditation.
Build 1.0 | Application | Guided Meditation | TS_02 | Verify the functionality of Guided Meditation | TC_02_02 | Verify that meditation files must be added successfully in the hosting services. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the meditation section. 4. Now verify that meditation files are successfully added in the hosting services. | Meditation files must added successfully in the hosting services. | Meditation files should be added successfully in the hosting services.
Build 1.0 | Application | Guided Meditation | TS_02 | Verify the functionality of Guided Meditation | TC_02_03 | Verify that API is successfully implemented for fetching meditation. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the meditation section. 4. User try to fetch meditation data. 5. Now verify that, API is implemented successfully for fetching meditation. | API must be implemented for fetching meditation. | API should be successfully implemented for fetching meditation.
Build 1.0 | Application | Guided Meditation | TS_02 | Verify the functionality of Guided Meditation | TC_02_04 | Verify that API is successfully implemented for playing meditation. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the meditation section. 4. Now verify that, API is implemented successfully for playing meditation. | API must be implemented for playing meditation. | API should be successfully implemented for playing meditation.
Build 1.0 | Application | Guided Meditation | TS_02 | Verify the functionality of Guided Meditation | TC_02_05 | Verify that player should be implemented successfully for meditation. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the meditation section. 4. Now verify that, player is implemented successfully for meditation. | Player must implemented successfully for meditation. | Player should be implemented successfully for meditation.
Build 1.0 | Application | Notification to take break at fix interval every day | TS_03 | Verify the functionality of Notification to take break at fix interval every day | TC_03_01 | Verify that database should be created successfully for break intervals. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the notifications section. 4. Now verify that, database for break intervals should be created. | Database must created successfully for break intervals. | Database should be created successfully for break intervals.
Build 1.0 | Application | Notification to take break at fix interval every day | TS_03 | Verify the functionality of Notification to take break at fix interval every day | TC_03_02 | Verify that API is implemented successfully for 'break notification' | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the notifications section. 4. Now verify that, API for 'break notifications' is successfully implemented. | API must be implemented successfully for 'break notification' | API should be implemented successfully for 'break notification'
Build 1.0 | Application | Notification to take break at fix interval every day | TS_03 | Verify the functionality of Notification to take break at fix interval every day | TC_03_03 | Verify that user interface for 'break notification' is designed successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the notifications section. 4. Now verify that, user interface for 'break notification' is designed successfully. | User interface for 'break notification' must be designed successfully. | User interface for 'break notification' should designed successfully.
Build 1.0 | Application | Notification to drink water at fix interval every day | TS_04 | Verify the functionality of Notification to drink water at fix interval every day | TC_04_01 | Verify that database has been successfully created for water reminder. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the notifications section. 4. Now verify that, database is successfully created for water reminder. | Database must successfully created for water reminder. | Database should be successfully created for water reminder.
Build 1.0 | Application | Notification to drink water at fix interval every day | TS_04 | Verify the functionality of Notification to drink water at fix interval every day | TC_04_02 | Verify that API is successfully implemented for water reminder notification. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the notifications section. 4. Now verify that, API is successfully implemented for water reminder notification. | API must successfully implemented for water reminder notification. | API should be successfully implemented for water reminder notification.
Build 1.0 | Application | Notification to drink water at fix interval every day | TS_04 | Verify the functionality of Notification to drink water at fix interval every day | TC_04_03 | Verify that user interface for 'water reminder notification' is designed successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. User navigates to the notifications section. 4. Now verify that, user interface for 'water reminder notification' is designed successfully. | User interface for 'water reminder notification' must be designed successfully. | User interface for 'water reminder notification' should designed successfully.

## Test case 3
Test Scenario ID | Test Scenario Summary | Test Case ID | Summary | Priority | Execution Type | Pre-condition | Detailed Steps | Post conditions | Expected Result
TS_01 | Verify the functionality of Set Goals | TC_01_01 | Verify that database for goals is created. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that database for goals is being created. | Database for goals must be created | Database for goals should be created
TS_01 | Verify the functionality of Set Goals | TC_01_02 | Verify that API for goals is implemented | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that API for goals is implemented. | API for goals must be implemented | API for goals should be implemented.
TS_01 | Verify the functionality of Set Goals | TC_01_03 | Verify that design is implemented correctly. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that design is being implemented correctly. | Design must be implemented correctly. | Design should be implemented correctly.
TS_01 | Verify the functionality of Set Goals | TC_01_04 | Verify that design user-interface is being completed. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that design user-interface is being completed. | Design user-interface must be completed. | Design user-interface should be completed.
TS_02 | Verify the functionality for Awards of Activities | TC_02_01 | Verify that database for awards is created. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that database for awards is being created. | Database for awards must be created. | Database for awards should be created.
TS_02 | Verify the functionality for Awards of Activities | TC_02_02 | Verify that API for awards is implemented | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that API for awards is implemented. | API for awards must be implemented | API for awards should be implemented.
TS_02 | Verify the functionality for Awards of Activities | TC_02_03 | Verify that design is implemented correctly for award of activities. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that design is implemented correctly for award of activities. | Design must be implemented correctly for award of activities. | Design should be implemented correctly for award of activities.
TS_02 | Verify the functionality for Awards of Activities | TC_02_04 | Verify that user-interface is being designed completely. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that User-interface design is being completely. | User-interface must be designed completely. | User-interface should be designed completely.
TS_03 | Verify the of Action recommendation for moods | TC_03_01 | Verify that database for actions is being implemented. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that database for action is being implemented. | Database for actions must be implemented. | Database for actions should be implemented.
TS_03 | Verify the of Action recommendation for moods | TC_03_02 | Verify that API for moods is implemented | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that API for moods is being implemented. | API for moods must be implemented | API for moods should be implemented
TS_03 | Verify the of Action recommendation for moods | TC_03_03 | Verify that user-interface is being designed completely for moods. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that user-interface is designed completely for moods. | User-interface must designed completely for moods. | User-interface should be designed completely for moods.
TS_03 | Verify the of Action recommendation for moods | TC_03_04 | Verify that design is implemented correctly for the moods. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that design is implemented correctly for moods. | Design must be implemented correctly for moods. | Design is implemented correctly for moods.
TS_04 | Verify the functionality for Personality Detection | TC_04_01 | Verify that database for actions is being created. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that database for actions must be created. | Database for actions must be created. | Database for actions should be created.
TS_04 | Verify the functionality for Personality Detection | TC_04_02 | Verify that API for personality detection is implemented successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that API for personality detection is implemented successfully. | API for personality detection must be implemented successfully. | API for personality detection should be implemented successfully.
TS_04 | Verify the functionality for Personality Detection | TC_04_03 | Verify that design is being implemented successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that design is being implemented successfully. | Design must be implemented successfully. | Design should be implemented successfully.

## Test case 4
Build | Module | Test Scenario Name | Test Scenario ID | Test Scenario Summary | Test Case ID | Summary | Priority | Execution Type | Pre- Condition | Detailed Steps | Post Condition | Expected Result
Build 1.0 | Application | Awards for activities | TS_01 | Verify the functionality of award for activities | TC_01_01 | Verify that database for awards is being created successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that database for awards is being created successfully. | Database for awards must be created successfully. | Database for awards should be created successfully.
Build 1.0 | Application | Awards for activities | TS_01 | Verify the functionality of award for activities | TC_01_02 | Verify that API for awards is being implemented successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that API for awards is being implemented successfully. | API for awards must be implemented successfully. | API for awards should be implemented successfully.
Build 1.0 | Application | Awards for activities | TS_01 | Verify the functionality of award for activities | TC_01_03 | Verify that user-interface has been designed successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that User-interface must be designed successfully. | User-interface must be designed successfully. | User-interface should be designed successfully.
Build 1.0 | Application | Awards for activities | TS_01 | Verify the functionality of award for activities | TC_01_04 | Verify that the design is being implemented successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that design is being implemented successfully. | The design must be implemented successfully. | The design should be implemented successfully.
Build 1.0 | Application | Action recommendation for moods | TS_02 | Verify the functionality of Action recommendation for moods. | TC_02_01 | Verify that database for depression action must be updated successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that database for depression action must be updated successfully. | Database for depression action must be updated successfully. | Database for depression action should be updated successfully.
Build 1.0 | Application | Action recommendation for moods | TS_02 | Verify the functionality of Action recommendation for moods. | TC_02_02 | Verify that API must be implemented to set if user is depressed. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that API must be implemented to set if user is depressed. | API must be implemented to set if user is depressed. | API should be implemented to set if user is depressed.
Build 1.0 | Application | MFA signin | TS_03 | Verify the functionality of MFA signin. | TC_03_01 | Verify that face ID login configuration is being done. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that Face ID login configuration must be done. | Face ID login configuration must be done. | Face ID login configuration should be done.
Build 1.0 | Application | MFA signin | TS_03 | Verify the functionality of MFA signin. | TC_03_02 | Verify that research implementation should be done successfully. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that Face ID login configuration must be done. | Research implementation must be done successfully. | Research implementation should be done successfully.
Build 1.0 | Application | Generic UI/UX | TS_04 | Verify the functionality of UI/UX | TC_04_01 | Verify that all the alignments are correct and data is properly visible. | High | Manual | User must have the right credentials to access the application. | 1. User enter the web application URL in the application. 2. User has landed on the to the web application. 3. Now verify that all the alignments are correct and data is properly visible. | All the alignments must be correct and data is properly visible. | All the alignments should be correct and data is properly visible.